## FallRecruitmentCampaign
Step to be completed | Days Before/ After | Event Date
FRC - Order Flyers and Posters | -200 | 2016-02-04
FRC - Identify top prospects for Chairs; identify volunteers to help recruit | -170 | 2016-03-05
FRC - Staff/Management meeting to prepare materials | -150 | 2016-03-25
FRC - Round Up Teams Recruited | -145 | 2016-03-30
FRC - Recruit Council and District Chairmen | -140 | 2016-04-04
FRC - Uniform discount promotion and brochure to printer | -135 | 2016-04-09
FRC - Prepare materials for Council Training: Family/Info/Parent Pak, Volunteer Indicator, Charter Partner Sponsor Kit, Flyer sample, Posters and Yard Signs (give to volunteers), review applications, fees and collections, Incentives (wristbands), Script, Sample Agenda for Orientation, review Program Preview Commitment Cards for Unit dates | -135 | 2016-04-09
FRC - Recruit Committee | -122 | 2016-04-22
FRC - Contact unit leaders (Packs and Troops) | -112 | 2016-05-02
FRC - Billboard Promotion | -100 | 2016-05-14
FRC - Recruit School Night Teams 100% | -98 | 2016-05-16
FRC - All materials for parents and leaders kits ready | -90 | 2016-05-24
FRC - VHS/DVD Production | -90 | 2016-05-24
FRC - Council Training of Units Use Charter Partner Promo Pak | -90 | 2016-05-24
FRC - Confirm Church Round-ups with church for Packs and Troops | -56 | 2016-06-27
FRC - Church bulletins to all churches (ScoutParents Charter Partner Promo Paks) | -35 | 2016-07-18
FRC - Unit Follow-up on Charter Partner Promo Paks - print bulletin inserts | -35 | 2016-07-18
FRC - Units have promotion materials to DE | -30 | 2016-07-23
FRC - Contact principals begins | -30 | 2016-07-23
FRC - All Units (Packs and Troops) trained | -30 | 2016-07-23
FRC - Check with principals on holding School Night Meeting at school - confirm in writing | -21 | 2016-08-01
FRC - Round-up boxes to staff | -21 | 2016-08-01
FRC - Round-up pre-flyers printed | -21 | 2016-08-01
FRC - School talks, school nights and open houses 100% set. Packs and Troops notified | -14 | 2016-08-08
FRC - Promotion to newspapers | -14 | 2016-08-08
FRC - Deliver pre-flyers and posters | -10 | 2016-08-12
FRC - Church round-ups complete | -7 | 2016-08-15
FRC - Final contact with teams | -7 | 2016-08-15
FRC - Hold Sign Up Night | -2 | #REF!
FRC - School Night completed | 0 | 2016-08-22
FRC - Thank you letter to principals | 7 | 2016-08-29
FRC - Tracking paperwork in | 7 | 2016-08-29
FRC - Set all second chance flyers | 14
FRC - Peer to peer effort begins | 21
Formulas:
Event Date = IF(C31>0,C31+[Days Before/ After]," ")

## DistrictActivity
Step to be completed | Days Before/ After | Pack Pinewood Derby | District Pinewood Derby
DACT - Meet with Program Chair to identify Event Chair | -160 | 2016-08-21 | 2016-08-28
DACT - Recruit Chairman, select committee | -140 | 2016-09-10 | 2016-09-17
DACT - Event Committee Meeting, Develop Budget and Program | -126 | 2016-09-24 | 2016-10-01
DACT - Event Committee promotes at Roundtable | -90 | 2016-10-30 | 2016-11-06
DACT - Event Committee Meeting Order patches, ribbons, supplies Mail information Facilities arranged | -84 | 2016-11-05 | 2016-11-12
DACT - Recruit Staff | -63 | 2016-11-26 | 2016-12-03
DACT - Event Committee promotes at Roundtable | -60 | 2016-11-29 | 2016-12-06
DACT - Promotion at Roundtable, email | -56 | 2016-12-03 | 2016-12-10
DACT - Event Committee Meeting Details completed Medical arrangements made | -42 | 2016-12-17 | 2016-12-24
DACT - Event Committee promotes at Roundtable | -30 | 2016-12-29 | 2017-01-05
DACT - Final program set | -14 | 2017-01-14 | 2017-01-21
DACT - Set Up | -14 | 2017-01-14 | 2017-01-21
DACT - Event | 0 | 2017-01-28 | 2017-02-04
DACT - Follow-up, Thank you, Budget final | 7 | 2017-02-04 | 2017-02-11
Formulas:
Pack Pinewood Derby = IF(C14>0,C14+[Days Before/ After]," ")
District Pinewood Derby = IF(D14>0,D14+[Days Before/ After]," ")

## RecharterProcess
Step to be completed | Days Before/ After | Event Date
RC - Recharter paperwork delivered to District Executive | -120 | 2016-08-03
RC - Recharter papers delivered to units | -90
RC - Recharter training of unit volunteers and commissioner for Online Recharter | -75 | 2016-09-17
RC - Recharter window opens Online | -60
RC - Charter review with Commissioners | -30 | 2016-11-01
RC - Recharters signed and money due to office | -15 | 2016-11-16
RC - Recharters due | 0 | 2016-12-01
RC - Unit Lapses | 1 | 2016-12-02
RC - Check on Charter Presentations | 30 | 2016-12-31
RC - Charter Presentations | 45 | 0
RC - Unit Drops | 60 | 2017-01-30
Formulas:
Event Date = IF(C8>0,C8+[Days Before/ After]," ")

## DistrictNominatingCommittee
Step to be completed | Days Before/ After | Event Date
DNOM - District Nominating Committee Chair meets with Council President and Council Nominating Committee Chair | -150 | 2016-08-16
DNOM - Confer with staff leader on potential nominating committee members | -120 | 2016-09-15
DNOM - Confer with district chairman on nominating committee members | -110 | 2016-09-25
DNOM - District chairman appoints nominating committee chairman | -90 | 2016-10-15
DNOM - Nominating committee chairman approved by council board | -90 | 2016-10-15
DNOM - District chairman appoints the balance of nominating committee | -60 | 2016-11-14
DNOM - District Executive prepares District Nominating Committee Worksheet | -60 | 2016-11-14
DNOM - District Chairman, Nominating Committee Chairman and DE meet | -58 | 2016-11-16
DNOM - Notification of first nominating committee meeting | -55 | 2016-11-19
DNOM - Check nominating committee meeting attendance | -47 | 2016-11-27
DNOM - First nominating committee meeting held | -45 | 2016-11-29
DNOM - Nominating committee contacts perspective district chairman and alternates, if necessary | -44 | 2016-11-30
DNOM - Check on nominating committee attendance | -37 | 2016-12-07
DNOM - Second nominating committee meeting held | -35 | 2016-12-09
DNOM - Confer with district chairman nominee on appointments of district operations committee chairman for next year | -30 | 2016-12-14
DNOM - Nominating Committee contact nominees for district vice- chairman, district committee and MAL | -25 | 2016-12-19
DNOM - District chairman nominee invites personnel to serve as district operations committee chairman | -20 | 2016-12-24
DNOM - All nominations confirmed | -15 | 2016-12-29
DNOM - Review nominating and election procedure with nominating committee chairman | -10 | 2017-01-03
DNOM - Nominating committee reports written | -7 | 2017-01-06
DNOM - Check final arrangements for District Annual Meeting | -1 | 2017-01-12
DNOM - Hold annual meeting | 0 | 2017-01-13
Formulas:
Event Date = IF(C23>0,C23+[Days Before/ After]," ")

## DistrictAnnualMeeting
Step to be completed | Days Before/ After | Event Date
DABM - Decide on location | -70 | 2016-11-04
DABM - Secure a meeting place | -70 | 2016-11-04
DABM - Check with nominating committee and Review annual meeting agenda | -49 | 2016-11-25
DABM - Prepare first meeting notice and turn in for approval | -42 | 2016-12-02
DABM - Mail annual meeting notice | -35 | 2016-12-09
DABM - Check with District Chairman and Operating Committee Members on annual meeting attendance, reports and assignments | -21 | 2016-12-23
DABM - Telephone calls to Charter Organization Representatives to secure attendance | -14 | 2016-12-30
DABM - Final check on physical arrangements | -7 | 2017-01-06
DABM - Hold District Annual Meeting | 0 | 2017-01-13
DABM - Register Committee Members and Members-At-Large | 7 | 2017-01-20
DABM - Follow - up and Thank -you's | 7 | 2017-01-20
Formulas:
Event Date = IF(C10>0,C10+[Days Before/ After]," ")

## DistrictAwardsSelectionComm
Step to be completed | Days Before/ After | Event Date
DAWC - Meet with District Chair to identify Awards Committee Chair | -100
DAWC - District Chairman recruits Awards Committee Chair | -70 | 2017-01-20
DAWC - District Chairman and Awards Committee Chair recruit committee | -56 | 2017-02-03
DAWC - Nomination forms distributed at Roundtables and District Committee meetings | -56 | 2017-02-03
DAWC - Meeting of Awards Committee; Applications reviewed and winners selected | -21 | 2017-03-10
DAWC - Awards and certificates are ordered | -19 | 2017-03-12
DAWC - Awards and certificates are obtained | -7 | 2017-03-24
DAWC - District Recognition Dinner held | 0 | 2017-03-31
DAWC - Media release and letters of congratulations sent | 7 | 2017-04-07
Formulas:
Event Date = IF(C9>0,C9+[Days Before/ After]," ")

## BoyScoutSpringRecruitment
Step to be completed | Days Before/ After | Event Date
BSSR - Get buy - in from Scoutmasters on Adventure Day and events | -60 | 2016-12-03
BSSR - Boy Fact Surveys completed on all fifth grade classes | -40 | 2016-12-23
BSSR - Letters with website & email address, boy scout brochure and troop info mailed to parents | -30 | 2017-01-02
BSSR - Boy Fact Survey to Scoutmasters for phone call follow - up separated by zip codes or schools | -30 | 2017-01-02
BSSR - School talks promoting Adventure Day | -5 | 2017-01-27
BSSR - Date of Adventure event or day | 0 | 2017-02-01
BSSR - Thank - you letters | 1 | 2017-02-02
BSSR - All applications into the office with dollars | 10 | 2017-02-11
BSSR - Track boys who attend Spring Camporee | 30 | 2017-03-03
BSSR - Track boys who attend Summer Camp | 90 | 2017-05-02
Formulas:
Event Date = IF(C7>0,C7+[Days Before/ After]," ")

## DistrictRecognitionBanquet
Step to be completed | Days Before/ After | Event Date
DRB - Meet with Program Chair to identify top prospects to recruit | -184 | 2016-09-28
DRB - Recruit Chairman | -154
DRB - Recruit Committee | -140 | 2016-11-11
DRB - Hold committee meeting and confirm date time and place | -119 | 2016-12-02
DRB - Develop budget | -119 | 2016-12-02
DRB - Program developed | -119 | 2016-12-02
DRB - Begin promotion of banquet | -119 | 2016-12-02
DRB - Mail "Save the Date" postcard (electronic) | -91 | 2016-12-30
DRB - Begin personal contacts | -49 | 2017-02-10
DRB - Mail invitation | -45 | 2017-02-14
DRB - Final check on physical arrangements | -42 | 2017-02-17
DRB - Printed program booklet designed | -42 | 2017-02-17
DRB - Order recognition items and ribbons | -42 | 2017-02-17
DRB - Finalize agenda assignments | -35 | 2017-02-24
DRB - Program finalized and printed | -14 | 2017-03-17
DRB - Finalize detailed agenda and review with chairman | -14 | 2017-03-17
DRB - Finalize meal plans and confirm final count | -7 | 2017-03-24
DRB - Setup for dinner | 0 | 2017-03-31
DRB - Hold dinner | 0 | 2017-03-31
DRB - Follow - up thank you's | 7 | 2017-04-07
Formulas:
Event Date = IF(C20>0,C20+[Days Before/ After]," ")

## DistrictCamporee
Step to be completed | Days Before/ After | Spring | Fall
DCMP - Meet with Program Chair to identify Camporee Chairman | -170 | 2016-11-02
DCMP - Recruit Chairman | -140 | 2016-12-02
DCMP - Recruit Committee | -133 | 2016-12-09
DCMP - Secure Location | -126 | 2016-12-16
DCMP - Hold Committee Meeting | -126 | 2016-12-16
DCMP - Promote with troops | -119 | 2016-12-23
DCMP - Hold Committee Meeting, develop program | -91 | 2017-01-20
DCMP - Develop recognition plan and patch | -91 | 2017-01-20
DCMP - Physical facilities arranged | -91 | 2017-01-20
DCMP - Have final budget approved by staff leader | -90 | 2017-01-21
DCMP - Committee promotes Camporee at Roundtable | -90 | 2017-01-21
DCMP - Mail Camporee Booklet | -60 | 2017-02-20
DCMP - Submit Camporee Booklet in electronic format to webmaster to post | -60 | 2017-02-20
DCMP - Committee promotes Camporee at Roundtable | -60 | 2017-02-20
DCMP - Recuest PO and order patches | -56 | 2017-02-24
DCMP - Arrange for religious observance | -49 | 2017-03-03
DCMP - Recruit judging personnel | -49 | 2017-03-03
DCMP - Lay out troop sites and plan assignments | -49 | 2017-03-03
DCMP - Advance publicity | -42 | 2017-03-10
DCMP - Committee promotes Camporee at Roundtable | -30 | 2017-03-22
DCMP - Prepare Camporee signs | -28 | 2017-03-24
DCMP - Develop Special Guest List, hold Committee meeting | -28 | 2017-03-24
DCMP - Arrange for first aid and hospital emergency service | -21 | 2017-03-31
DCMP - Arrange for HQ setup | -21 | 2017-03-31
DCMP - Arrange facilities for Trading Post, PA System, etc., if needed | -14 | 2017-04-07
DCMP - Complete details for final program bulletin; reproduce and mail | -14 | 2017-04-07
DCMP - Plan evening program and assign responsibilities | -14 | 2017-04-07
DCMP - Pick - up materials and take to site | -7 | 2017-04-14
DCMP - Set- up | 0 | 2017-04-21
DCMP - Hold Camporee | 0 | 2017-04-21
Formulas:
Spring = IF(C31>0,C31+[Days Before/ After]," ")
Spring = IF(C31>G20,C31+[Days Before/ After]," ")

## DistrictDayCamp
Step to be completed | Days Before/ After | Event Date
DDC - Meet with Program Chairs to identify directors | -300 | 2016-08-25
DDC - Select Day Camp Director and Program Director | -280 | 2016-09-14
DDC - Camp School dates and forms to directors | -250 | 2016-10-14
DDC - Day Camp Meeting - discuss program, dates, staff, budget, fees and camp school dates | -240 | 2016-10-24
DDC - Meet with Directors to identify staff | -210 | 2016-11-23
DDC - Select and Secure Site and date, send in material for promotion, secure transportation | -200 | 2016-12-03
DDC - Deadline for site, date and director information to Council Office for production of Day Camp Brochure and Camp Promotion material | -189 | 2016-12-14
DDC - Key Staff recruited | -150 | 2017-01-22
DDC - Council Day Camp meeting - Review draft of brochure, t-shirt, patch design | -150 | 2017-01-22
DDC - Camp Promotion Begins by Day Camp Staff at Roundtables, Blue and Gold Banquets, Individual Pack meetings | -145 | 2017-01-27
DDC - Brochure to printer | -121 | 2017-02-20
DDC - Director and Program Director to Council Day Camp Administration Meeting | -107 | 2017-03-06
DDC - Train Key Staff, plan program themes, develop staff manual | -100 | 2017-03-13
DDC - Brochures printed and mailed | -100 | 2017-03-13
DDC - Follow up meeting with Council Day Camp Chair and directors | -90 | 2017-03-23
DDC - Order craft and material items | -90 | 2017-03-23
DDC - Staff meeting for planning of unit visitations and promotion | -90 | 2017-03-23
DDC - Staff meeting, finalize manual | -60 | 2017-04-22
DDC - Order patches | -56 | 2017-04-26
DDC - Precamp Inspection | -30 | 2017-05-22
DDC - T-shirt sizes and quantity; patch numbers to office | -30 | 2017-05-22
DDC - Staff Training on site for den leaders and helpers; Parent's meeting | -7 | 2017-06-14
DDC - Set Up | -1 | 2017-06-20
DDC - Day Camp | 0 | 2017-06-21
DDC - Camp Visitation | 1 | 2017-06-22
DDC - Day Camp Review | 7 | 2017-06-28
DDC - Director and Program Director to Council Day Camp Administration Meeting for final review and evaluation. Promotion pictures and overall theme to be determined. | 75 | 2017-09-04
Formulas:
Event Date = IF(C25>0,C25+[Days Before/ After]," ")

## DistrictProgramKickofff
Step to be completed | Days Before/ After | Event Date
DPPC - Secure location | -70 | 2016-03-03
DPPC - Develop program with Key 4 | -70 | 2016-03-03
DPPC - Promote at Roundtable and other district meetings | -70 | 2016-03-03
DPPC - Submit final agenda for Program Preview Conference to supervisor and camp | -60 | 2016-03-13
DPPC - Order supplies from office | -60 | 2016-03-13
DPPC - Conference notice prepared and mailed | -35 | 2016-04-07
DPPC - Program assignments reviewed with district operating committee chairman, finalize agenda and make assignments | -35 | 2016-04-07
DPPC - Assemble all materials | -30 | 2016-04-12
DPPC - Follow - up with program presenters | -14 | 2016-04-28
DPPC - Telephone calls to unit leaders inviting them to event | -14 | 2016-04-28
DPPC - Final check on facility | -7 | 2016-05-05
DPPC - Setup and hold conference | 0 | 2016-05-12
DPPC - Follow - up | 7
Formulas:
Event Date = IF(C13>0,C13+[Days Before/ After]," ")

## ScoutingForFood
Step to be completed | Days Before/ After | Event Date | Event Date
SFF - Identify sponsor for event and volunteer to assist in recruitment | -180 | 2016-08-29
SFF - Secure sponsor for event | -180 | 2016-08-29
SFF - Identify top prospects for chair and volunteers to assist in recruitment | -180 | 2016-08-29
SFF - District Committee identifies plans and prospects | -180 | 2016-08-29
SFF - Secure Council Chairman for Scouting for Food | -150 | 2016-09-28
SFF - District Scouting for Foods Chairs secured | -130 | 2016-10-18
SFF - Invitations sent for Oreintation | -130 | 2016-10-18
SFF - Arrangements made for Scouting for Food bags | -120 | 2016-10-28
SFF - Arrangements made for Drop Off Locations | -120 | 2016-10-28
SFF - Arrangements made for Delivery Trucks | -120 | 2016-10-28
SFF - Orientation for all Chairs | -100 | 2016-11-17
SFF - Communication with District personnel | -90 | 2016-11-27
SFF - Order Patches | -60 | 2016-12-27
SFF - Information to Unit Leaders through Roundtable and email | -60 | 2016-12-27
SFF - Good Turn for America ID's available | -45 | 2017-01-11
SFF - Bags and maps to Unit Leaders | -30 | 2017-01-26
SFF - Bags placed by units | -7 | 2017-02-18
SFF - Scouting for Food | 0 | 2017-02-25
SFF - Follow up with units on submitting Good Turn for America | 7 | 2017-03-04
SFF - Thanks you letters | 7 | 2017-03-04
SFF - Follow up and Evaluation Meeting | 14 | 2017-03-11
Formulas:
Event Date = IF(C19>0,C19+[Days Before/ After]," ")

## SpringRecruitment
Step to be completed | Days Before/ After | Event Date
SPRING - Identify units that will do Spring Roundup - Packs and Troops | -120 | 2016-11-01
SPRING - Start production of DVD (BP logo) | -113 | 2016-11-08
SPRING - Identify newspapers for promotion | -113 | 2016-11-08
SPRING - Confirm participating Packs, Troops and Churches | -79 | 2016-12-12
SPRING - Notice to principals on Spring Round Up Plan | -79 | 2016-12-12
SPRING - Have Family Paks prepared, packets prepared, flyers printed | -75 | 2016-12-16
SPRING - Round Up boxes prepared | -75 | 2016-12-16
SPRING - DVD's to Staff with flyer template (BP logo) | -32 | 2017-01-28
SPRING - All pre-notices and talks complete | -22 | 2017-02-07
SPRING - All Spring Round-ups | -20 | 2017-02-09
SPRING - Follow up notice to Tigers on Fishing Day | -17 | 2017-02-12
SPRING - All applications into office with leader's signatures | -17 | 2017-02-12
SPRING - All Tigers Rounded Up | 0 | 2017-03-01
SPRING - Day Camp | 15 | 2017-03-16
SPRING - All Tigerss called to make sure in unit and active (by Commissioners) | 25 | 2017-03-26
SPRING - Send postcards to Tigers about Tiger Day | 30 | 2017-03-31
SPRING - Send postcards to Cub Scouts about Resident Camp | 30 | 2017-03-31
SPRING - All Tigers registered in ScoutNET | 30 | 2017-03-31
SPRING - Tiger Day | 70 | 2017-05-10
Formulas:
Event Date = IF(C14>0,C14+[Days Before/ After]," ")